## Regression Checklist
ID | Area | Scenario | Expected Result | Actual Result | Status | Evidence / Notes | Blocking
REG-001 | Release Structure | Single executable root | One index, one CSS, one JS, approved assets and docs only | Single clean runtime produced | PASS | Static package inventory | No
REG-002 | Release Structure | Nested/legacy cleanup | No nested ZIPs, duplicate builds, dead JS or legacy artifacts | None found | PASS | Static archive scan | No
REG-003 | Content | Candidate B content preservation | No substantial Candidate B learning segment lost | 149 substantial segments preserved | PASS | Normalized main-content comparison | No
REG-004 | Content | Verified cases | Lviv, Rotterdam, Amsterdam and Leuven remain present | All preserved | PASS | DOM text inventory | No
REG-005 | Content | Official URLs | All Candidate B official/external URLs remain | 10 of 10 preserved | PASS | Href inventory | No
REG-006 | Assets | Approved PNG integrity | All three assets byte-identical | All hashes match | PASS | SHA-256 comparison | No
REG-007 | HTML | Page sequence | Pages open in order 1–10 with no orphan page | Continuous 1–10 sequence | PASS | DOM/static check | No
REG-008 | HTML | Heading hierarchy | One H1 on every lesson page | 10 of 10 pages compliant | PASS | DOM/static check | No
REG-009 | HTML | Duplicate IDs | No duplicate element IDs | None found | PASS | DOM/static check | No
REG-010 | Navigation | Sequential controls | Previous/next route correctly | Passed | PASS | Controlled Chromium | No
REG-011 | Navigation | Browser Back/Forward | History restores page 9 and page 10 correctly | Passed | PASS | Controlled Chromium | No
REG-012 | Navigation | Semantic adjacent lessons | No learner-facing Lesson 01/Lesson 03 numeric transitions | None found | PASS | DOM text scan | No
REG-013 | Progress | Percentage semantics | Visual percent equals aria-valuenow 0–100 | 10–100% verified | PASS | Controlled Chromium | No
REG-014 | Progress | Completion state | Page 10 after passed test persists completed=true | Passed | PASS | Controlled Chromium/localStorage | No
REG-015 | Progress | Furthest progress | Going backward does not reduce completed progress | 100% retained after Back | PASS | Controlled Chromium | No
REG-016 | Reset | Controlled reset | Clear progress/test/scenarios; preserve Portfolio/case notes | Passed | PASS | Controlled Chromium | No
REG-017 | Interactive | Completion gate | Cannot leave page 6 until all three situations completed | Passed; no bypass control | PASS | Controlled Chromium | No
REG-018 | Interactive | Persistence | Scenario selections and completion restore | Passed | PASS | Controlled Chromium/localStorage | No
REG-019 | Assessment | Test gate | Page 10 remains locked before five correct answers | Passed | PASS | Controlled Chromium | No
REG-020 | Assessment | Feedback | Each question provides correct/try-again explanation | Passed | PASS | Controlled Chromium | No
REG-021 | Portfolio | Autosave and restore | All learner fields persist after reload | Passed | PASS | Controlled Chromium/localStorage | No
REG-022 | Portfolio | Summary | Saved fields render in Portfolio Summary | Passed | PASS | Controlled Chromium | No
REG-023 | Portfolio | Transfer protection | Occupied principles are not silently overwritten | Merge/replace/cancel dialog shown | PASS | Controlled Chromium | No
REG-024 | Portfolio | PDF | Local PDF downloads with Portfolio field mapping | Valid PDF generated | PASS | Controlled Chromium/download evidence | No
REG-025 | AI Assistant | Facts mode | Independent facts/assumptions prompt, no rewrite instruction | Passed | PASS | Prompt text check | No
REG-026 | AI Assistant | Questions mode | Independent 1–3 questions prompt, no rewrite instruction | Passed | PASS | Prompt text check | No
REG-027 | AI Assistant | Structure mode | Independent completeness/weakness prompt, no rewrite instruction | Passed | PASS | Prompt text check | No
REG-028 | AI Assistant | Preview dialog | Preview opens in labeled native dialog and restores focus | Passed | PASS | Controlled Chromium | No
REG-029 | AI Assistant | Copy UX | Inline and dialog copy show “Скопійовано” | Passed | PASS | Controlled Chromium | No
REG-030 | AI Assistant | Platform links | Only ChatGPT and Gemini actions provided | Passed | PASS | DOM link inventory | No
REG-031 | Images | Zoom coverage | Hero and both infographics open in lightbox | 3 of 3 passed | PASS | Controlled Chromium | No
REG-032 | Images | Lightbox controls | ESC and backdrop close; focus returns | Passed | PASS | Controlled Chromium | No
REG-033 | Accessibility | Accessible names | No unnamed button/link/input/textarea/select | None found | PASS | Live DOM audit | No
REG-034 | Accessibility | Dialog labels | All dialogs have aria-labelledby targets | 3 of 3 passed | PASS | Live DOM audit | No
REG-035 | Accessibility | Focus visibility | Page/dialog/image focus remains visible and restored | Passed | PASS | Controlled Chromium/visual review | No
REG-036 | Mobile | Viewport width | No horizontal overflow at 375 px | Passed | PASS | Controlled Chromium metrics | No
REG-037 | Mobile | Heading wrapping | No mid-word/viewport overflow | Passed | PASS | Controlled Chromium metrics/visual review | No
REG-038 | Mobile | Page labels | Compact labels fit the header | Passed | PASS | Controlled Chromium metrics | No
REG-039 | Runtime | JavaScript syntax | Node syntax validation returns no error | Passed | PASS | node --check | No
REG-040 | Runtime | Console errors | No warning/error/exception during full flow | None recorded | PASS | Controlled Chromium console | No

## Summary
UCAN Lesson 02 — Gold Release Candidate v2.0
Release status | Gold Release Candidate QA Passed
Production role | Production Reference v2
QA date | 2026-07-26
Total regression checks | 40
Passed | 40
Failed | 0
Known application defects | 0
Deployment requirement | Final smoke test on intended HTTP/HTTPS origin